## Cover Page
OutReach App
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project solutions
Role
Signature
| Date | 2019-12-15
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Backlog
Product Backlog Outreach App Project ID: B022 C3: Protected Controlled Copy
Done
Volunteer Story Id | Volunteer Story Name | Volunteer Story Role | Volunteer Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Initial Selection | Admin/Volunteer | As Admin/volunteer I want the system to allow to Admin/Volunteer to choose Admin/Volunteer Login/Registration | 1-Screen should display the option for Admin login / Registration and Volunteer login / Registration | 1 | 1 | Yes | 1 | 1 | 1
US_2 | Volunteer Registration | Volunteer | As Volunteer I want the system to procure the fundamental details of the Volunteer | 1-When the Volunteer clicks on the registration link, it should re-direct to registration form. 2-Volunteer needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, Volunteer Id, Password Clicking ‘Submit’ should validate the datatype constraints for each field 3-Volunteer failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Post-successful field level validation, save the information in the database 5-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | 1 | 5 | Yes | 1 | 1 | 5
US_3 | Volunteer Authentication | Volunteer | As Volunteer I want the system to authenticate the Volunteer credentials of the registered Volunteer | 1-A registered Volunteer – is able click ‘Login’ link, after keying in ‘Volunteer ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | 1 | 3 | Yes | 1 | 1 | 3
US_4 | Admin Registration | Admin | As Admin I want the system to procure the fundamental details of the Admin | 1-When the Admin clicks on the registration link, it should re-direct to registration form. 2-Admin needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, Vendor Id, Password Clicking ‘Submit’ should validate the datatype constraints for each field 3-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Post-successful field level validation, save the information in the database 5-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | 1 | 5 | Yes | 1 | 1 | 5
US_5 | Admin Authentication | Admin | As Admin I want the system to authenticate the credentials of the registered Admin | 1-A registered Volunteer – is able click ‘Login’ link, after keying in ‘Admin ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | 1 | 3 | Yes | 1 | 1 | 3
US_6 | Create Event | Admin | As Admin I want the system to allow Admin to create Events | 1-Admin upon clicking Create Event should redirect to Event creation page 2-Admin can provide the below information and click submit. Activiy,decription,place,date,contact number 3-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please provide the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Upon checking the information in the database, display the message ‘Details updated successfully’. | 1 | 5 | Yes | 1 | 1 | 5
US_7 | View / join Event | Volunteer | As Volunteer I want the system to allow Volunteer to view / join Events | 1-Volunteer can view the list of available event from the current date upto next 15 days’ event 2-Volunteer can use filter to check any particular events based on location/event type 3-Clicking on “Join” Volunteer can join the event. Volunteer can invite their colleague to participate in an event. 4-Clicking on “Invite ” link Volunteer can invite their colleague. | 1 | 8 | Yes | 1 | 1 | 8
US_8 | Volunteer Attendance | Admin | As Admin I want to register Volunteers' attendance on the event presence. | 1-Admin should be able to mark the attendance of the volunteer, if he is present for an event. | 1 | 8 | Yes | 1 | 1 | 8
US_9 | Wah account | Admin | As Admin I want to give Wah points to the volunteer | 1-When the volunteer is present for an event, wah points should be added to their wah account Wah points should be based on the activity the volunteer is participating 2-Below are the Wah points list 50- activities within the premisis, like beautifying the nursery, greeting cards for 12std students etc 100- for seed ball making, on weekend 200- teaching in government school 300 – beach clean up 400 – planting trees 500 – weekend farming | 2 | 8 | Yes | 1 | 1 | 8
US_10 | Donation for the event | Volunteer | As Volunteer I want the system to collect the donation from the volunteer. | 1-Volunteer can donate money for any event activity. 2-Admin can view the collected donation from all volunteers. 3-Admin can transfer the donation to the outreach event organizer. 4-Clicking on ”Donate” Volunteer lead to the money transaction page 5-Clicking on ”Donate” admin lead to the money transaction page. | 2 | 13 | No | 1 | 1 | 13
US_11 | Event Schedule and Invite | Volunteer | As Volunteer I want the system to generate visit event schedule and invite others. | 1-Volunteer can see the event schedule when he/she join to that event. 2-Schedule page provide all mandatory information (date, time, number of volunteer, place, contact number) for that event. 3-Admin provide event schedule details with all mandatory information | 2 | 5 | Yes | 1 | 1 | 5
US_12 | Volunteer / Admin Log off | Volunteer/Admin | As Volunteer/AdminI want the system to disconnect from the application on clicking log off. | 1-Option to log off from the system. | 2 | 1 | Yes | 1 | 1 | 1

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000