## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Outreach app Project ID: B022 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Initial Selection | 1
Task_1 | Design the Home page |  | Sachin Guldagad | completed | 3 | 1 | 0.5 | 0.5 | 0 | 0
User Story #2 | Volunteer Registration | 5
Task_1 | Design the Volunteer registration page |  | Vinay | completed | 3 | 2 | 0.5 | 1 | 0 | 0
Task_2 | Validate the input fields |  | Sachin Guldagad | completed | 3 | 2 | 1 | 0 | 0 | 0
Task_3 | Create table for storing volunteer registration details |  | Tejas | completed | 6 | 3 | 5 | 0 | 0 | 0
Task_4 | Develop code to store the Volunteer details |  | Nayan | completed | 7 | 5 | 2 | 1 | 0 | 0
User Story #3 | Volunteer Authentication | 3
Task_1 | Design the Volunteer login page |  | Sachin Gadale | completed | 3 | 1 | 1 | 0.5 | 0 | 0
Task_2 | Validate the volunteer checking the databse |  | Nayan | completed | 4 | 2 | 2 | 1 | 0 | 0
User Story #4 | Admin Registration | 5
Task_1 | Design the admin registration page |  | Vinay | completed | 3 | 1 | 0.5 | 0 | 0 | 0
Task_2 | Validate the input fields |  | Sachin Guldagad | completed | 3 | 0.5 | 0.5 | 1 | 0 | 0
Task_3 | Create table for storing admin registration details |  | Tejas | completed | 4 | 2 | 1 | 0.5 | 0 | 0
Task_4 | Develop code to store the admin details |  | Tejas | completed | 2 | 1 | 1 | 0.5 | 0 | 0
User Story #5 | Admin Authentication | 3
Task_1 | Design the admin login page |  | Sachin Gadale | completed | 2 | 1 | 0.5 | 1 | 0 | 0
Task_2 | Validate the admin checking the databse |  | Sachin Guldagad | completed | 2 | 1 | 0.5 | 0.5 | 0 | 0
User Story #6 | Create Event | 3
Task_1 | Design the Event creation page |  | Vinay | completed | 2 | 1 | 1 | 0 | 0 | 0
Task_2 | Get Event details from admin |  | Nayan | completed | 3 | 0.5 | 0.5 | 1 | 0 | 0
Task_3 | Validate the Event details |  | Vinay | completed | 3 | 1 | 0 | 1 | 0 | 0
Task_4 | Add the event to the database |  | Tejas | completed | 7 | 2 | 2 | 1 | 0 | 0
User Story #7 | View / join Event | 3
Task_1 | Query the database for events |  | Nayan | completed | 9 | 3 | 2 | 2.5 | 0 | 0
Task_2 | Query database based on filters applied |  | Nayan | completed | 6 | 3 | 2 | 2 | 0 | 0
Task_3 | Register volunteer for an event |  | Sachin Gadale | completed | 3 | 2 | 1 | 1 | 0 | 0
Task_4 | Provide option for volunteer to invite others |  | Sachin Gadale | completed | 3 | 1 | 1 | 0 | 0 | 0
User Story #8 | Volunteer Attendance | 3
Task_1 | Design the attendance sheet |  | Tejas | completed | 4 | 1 | 0.5 | 0.5 | 0 | 0
Task_2 | Push the attendance to database |  | Tejas | completed | 5 | 2 | 1 | 0.5 | 0 | 0
TOTAL |  |  |  |  | 90 | 22.5 | 16 | 7.5 | 0 | 0

## Sprint -2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Wah Account | 5
Task_1 | Create the page to add Wah Points |  | Vinay | Completed | 3 | 1 | 0.5 | 1.5 | 0 | 0
Task_2 | Display the Wah points list |  | Tejas | Completed | 4 | 1 | 1 | 0.5 | 0 | 0
Task_3 | Add Wah points to the Wah account of Volunteer |  | Nayan | Completed | 4 | 2 | 1 | 2 | 0 | 0
Task_4 | Query the Wah points in Database |  | Nayan | Completed | 5 | 2 | 3 | 0 | 0 | 0
User Story #2 | Donation for the Event | 5
Task_1 | Create Page for Donation for an Event |  | Sachin Gadale | Completed | 3 | 1 | 0.5 | 2 | 0 | 0
Task_2 | Create donate button for Volunteer which will lead to the money transaction page |  | Tejas | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_3 | Create page by which admin is able to donate to outreach event |  | Vinay | Completed | 2 | 0.5 | 1 | 1 | 0 | 0
Task_4 | Admin should be able to view donation for the respective event |  | Sachin Gadale | Completed | 3 | 1 | 2 | 1 | 0 | 0
User Story #3 | Event Shedule and invite | 5
Task_1 | Provite button to see the shedule for different events when he/she joins the event |  | Sachin Guldagad | Completed | 2 | 0.5 | 1 | 1 | 0 | 0
Task_2 | Display all the mandatory information related to event |  | Vinay | Completed | 3 | 1 | 2 | 1 | 0 | 0
Task_3 | Update the database on creation of any new event |  | Nayan | Completed | 5 | 2 | 3 | 2 | 0 | 0
Task_4 | Volunteer should be successfully able to invite other collegues for the event |  | Tejas | Completed | 4 | 1 | 0.5 | 1 | 0 | 0
User Story #4 | Volunteer/Admin Log off | 3
Task_1 | Provide Option to log off from the system |  | Sachin Guldagad | Completed | 2 | 1 | 0 | 1 | 0 | 0
Task_2 | Redirect to home page on Log Off |  | Sachin Guldagad | Completed | 1 | 1 | 0 | 0 | 0 | 0
TOTAL |  |  |  |  | 43 | 16 | 16.5 | 14 | 0 | 0

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A